## 1. Contract Inventory
Contract Inventory
Today's Date | 2018-02-05
Key Contract Data
[5 empty] | Date Contract |  | Contract Term |  | Renewal Notice |  |  |  | Country |  | Est Annual Value |  | Key Contacts
Supplier Name | Contract Name | Contract Type | Services Category | Services Provided | Starts | Ends | Duration | D/W/M/Y | Date | Days Away | Status | Key? | Where Signed | Law Applies | Currency | Amount | Buyer | Supplier
eg. ABC Corp | IT Security Testing 15 May 2017 | MSA | IT Security | IT security testing | 2017-01-01 | 2018-12-31 | 2 | Y | 2018-11-30 | 298 | Active | Y | Australia | Texas USA | USD | 200000 | F Bloggs | P Smith
Template by Gatekeeper
Note on M11: Rod Linsley: Y if this is a key contract else blank
What's it for?
Record basic details of all contracts within your business

## 2. Confidential Info Register
Confidential Information Register |  |  |  |  | Confidential Information Disclosed
|  |  | Contract Dates |  | To Supplier |  |  |  | To Buyer
# | Supplier Name | Contract Name | Start | End | Nature of Info | How Disclosed | At End of Term | Done? | Nature of Info | How Disclosed | At End of Term | Done?
1 | eg. ABC Corp | IT Security Testing 15 May 2017 | 2017-07-01 | 2018-06-30 | Custom server build process | Softcopy | Return
Template by Gatekeeper
Note on G8: Gatekkeeper Guidance: Hardcopy, softcopy, software, hardware device
Note on I8: Gatekeeper Guidance Confirm that end of contract action completed
What's it for?
Identify all Confidential Information disclosed by each party to a contract, to allow compliance with end-of-contract return or destruction obligations

## 3. Contract Change Log
Contract Change Log
| Contract |  |  | Change
Supplier Name | Name | From | Change # | Req # | Outline | Date
eg. ABC Corp | IT Security Testing 15 May 2017 | Buyer | 6 | 82 | Update pricing schedules for 2018 | 2017-12-15
Template by Gatekeeper
What's it for?
Record summary details of every change made to every contract, to allow Contract Management workload analysis and contract volatility tracking

## 4. Disputes Log
Contract Disputes Log
|  |  | Dispute |  |  |  |  | Resolution |  |  | Managed By
# | Supplier Name | Contract Name | Date | Details | Notifier | Severity | Status | Date | For | Details | For Buyer | For Supplier
1 | eg. ABC Corp | IT Security Testing 15 May 2017 | 2018-01-01 | Supplier alleged to have deliberately charged for services not delivered Q4 2017 | Buyer | High | Resolved | 2018-01-10 | Buyer | Supplier investigations revealed fraudulent activitiy in its Finance team. Staff sacked, corrected invoices reissued | F Bloggs | P Smith
Template by Gatekeeper
What's it for?
Record details of all formally notified disputes, their progress and any resolution details, to allow relationship volatility tracking

## 5. Events Calendar
Contract Events Calendar
Event
Supplier Name | Contract Name | Due On | Details
eg. ABC Corp | IT Security Testing 15 May 2017 | 2018-04-01 | Advise supplier if contract will be renewed or terminated
Template by Gatekeeper
What's it for?
Record details of all date-driven contract events and associated supporting events, to allow Contract Management workload planning and monitoring

## 6. IP Rights Register
Intellectual Property Rights Register
Supplier Name |  | eg. ABC Corp
Contract Name |  | IT Security Testing 15 May 2017
Date Contract Signed |  | 2017-05-31
Pre-existing IP To Be Used
| Buyer's | Custom server build process
Supplier's
New IP To Be Transferred To |  |  | Date
| Buyer | Supplier's updates to custom server build process |  | Supplier Use Of New IP Allowed | For contract term
| Supplier |  |  | Buyer Use Of New IP Allowed
Template by Gatekeeper
Note on F14: Gatekeeper Guide: No For Contract Term Perpetually
What's it for?
Identify all pre-existing IP to be used and any new IP to be assigned under a contract, to allow Legal workload planning

## 7. Issues Log
Contract Issues Log
|  |  | Issue |  |  |  |  | Resolution |  |  | Managed By
# | Supplier Name | Contract Name | Date | Details | Notifier | Severity | Status | Date | For | Details | For Buyer | For Supplier
1 | eg. ABC Corp | IT Security Testing 15 May 2017 | 2017-06-01 | Friction between onsite supplier staff | Buyer | Low | Resolved | 2017-06-15 | Buyer | At-fault supplier staff replaced | F Bloggs | P Smith
Template by Gatekeeper
What's it for?
Record details of all contract-related issues, their progress and any resolution details, to allow contract and relationship volatility tracking

## 8. Lessons Learned Register
Lessons Learned Register
# | Date | Subject Matter Category | Situation Details | Root Cause | Lessons Learned | Keywords (for easy search)
1 | 2017-06-30 | eg. User satisfaction surveys | Supplier strongly disputed that service delivery performance was problematic | Staff members shared their completed survey form with the supplier | 1. Never assume that staff understand what is and isn't confidential 2. Clearly mark all such surveys as 'not to be shared with supplier' and reiterate the message on all emails to survey participants | User satisfaction survey Confidential
Template by Gatekeeper
What's it for?
Record details of every lesson learned from various situations during the course of business, to provide guidance for the future

## 9. Loaned Items Register
Loaned Items Register
Supplier Name
Contract Name
Date Signed
Loaned Items |  |  |  |  | Not Returned
Loaned By | Description | Date Loaned | Loan Period | Date Returned | Reason | Consequence
eg. Buyer | 1 x Dell Latitude E7470 notebook, S/N 123456 1 x building access card, no. 7524 | 2017-09-18 | 12 months
Template by Gatekeeper
What's it for?
Identify all items loaned by one party to the other during the term of a contract, to ensure the return of those items when due, or payment of any compensation otherwise

## 10. Contract Management Plan
Contract Management Plan
Supplier Name | Contract Name
Lifecycle Stage | Activity | Frequency
Start-up | eg. Onsite kick-off meeting | One-off
Template by Gatekeeper
Note on A11: Rod Linsley: initiation, negotiation, execution, start-up, operation, renewal, close-out
What's it for?
Record the key high-level activities planned for managing a contract, to allow Contract Management workload planning

## 11. Obligations Compliance Log
Obligations Compliance Checking Log
Supplier Name
Contract Name
Obligation |  |  | Checked |  |  | Non-Compliance
Subject Matter | Description | Applies To | Date | By | Outcome | Issues Found | Actions Taken
eg. Payment | No tax invoices to be issued by supplier later than 180 days after provision of the applicable goods and / or services | Supplier | 2018-01-15 | F Bloggs | Non-Compliant | 26 instances of such invalid tax invoices discovered by AP during the measurement period | Invoices not paid. Supplier officially warned about unacceptable behaviour
Template by Gatekeeper
Note on F12: Rod Linsley: eg compliant part compliant non-compliant
What's it for?
Identify each party's individual and joint contract obligations and rights, to allow Contract Management workload planning and monitoring

## 12. Outstanding Matters Summary
Oustanding Contract Matters Summary
Supplier Name
Contract Name
Date Signed
Outstanding Matter |  |  |  | Date |  | Applicable Contract
Category | Applicable Clause # | Description | Reason | To Be Addressed | Addressed | Change Request #
eg. SLA implementation | Section E, cl 26-32 | SLA ramp-up timing needs to be finalised | Network inventory analysis needs to be finalised so roll-out plan can be completed | 2018-03-30
Template by Gatekeeper
Note on G13: Rod Linsley: Identify the contract change used to formally record the conclusion of the outstanding matter
What's it for?
Identify all contract matters to be addressed post-execution, to allow Contract Management workload planning and contract finalisation

## 13. Risk Register
Contract Risk Register
Supplier Name |  | Contract Name
eg. ABC Corp |  | IT Security Testing 15 May 2017
[10 empty] | Mitigation Actions |  |  |  | Likelihood+Consquence | Risk Level
Risk |  |  |  | Rating If Risk Uncontrolled |  |  | Rating If Risk Managed |  |  | Preventative |  | Contingency |  | almostcertainextreme | Extreme
# | Category | Details | Impact | Likelihood | Consequence | Risk Level | Likelihood | Consequence | Risk Level | Actions | Assigned To | Actions | Assigned To | almost certainhigh | Extreme
1 | Supplier Performance | eg. Supplier can't always deliver desired services as required and promised | Project schedule delays and cost overrruns | Possible | High | High | Unlikely | Low | Moderate | Closely track supplier's conformance to delivery schedule and SLAs, establish levels of drift that trigger consultations with supplier | Buyer and Supplier | Escalate the issue with senior supplier management, invoke liquidated damages provisions of the contract and apply SLA breach penalties |  | almost certainlow | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | almost certainmoderate | Extreme
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | almost certainnegligible | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | likelyextreme | Extreme
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | likelyhigh | Extreme
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | likelylow | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | likelymoderate | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | likelynegligible | Moderate
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | possibleextreme | Extreme
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | possiblehigh | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | possiblelow | Moderate
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | possiblemoderate | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | possiblenegligible | Moderate
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | rareextreme | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | rarehigh | Moderate
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | rarelow | Low
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | raremoderate | Moderate
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | rarenegligible | Low
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | unlikelyextreme | Extreme
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | unlikelyhigh | High
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | unlikelylow | Moderate
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | unlikelymoderate | Moderate
[6 empty] | #N/A |  |  | #N/A |  |  |  |  | unlikelynegligible | Low
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
[6 empty] | #N/A |  |  | #N/A
Template by Gatekeeper
Note on B12: Rod Linsley: eg financial, operational
Note on E12: Rod Linsley: rare unlikely possible likely almost certain
Note on F12: Rod Linsley: negligible low moderate high extreme
Note on G12: Rod Linsley: calculated
Note on L12: Rod Linsley: buyer, supplier, both
What's it for?
Identify and rank every potential risk for a contract and associated mitigation strategies, to allow periodic risk profile review and any mitigation adjustments